## Slide 1: Comprehensive, Collaborative System of Crisis and Emergency Care
An objective review for the feasibility of a regional psychiatric emergency facility
Jeffrey Geppert
Senior Research Leader
Advanced Analytics and Health Research
Mary Sheehan
Research Scientist
Advanced Analytics and Health Research

## Slide 2: Overview
Review of the overall project
Progress to date
Next Steps
Questions and Answers

## Slide 3: Project Summary
Provide objective, technically-based analysis and project facilitation to determine the feasibility of a regional psychiatric emergency facility
  Coordinate studies to validate assumptions on clinical need, reimbursement outlook, and facility cost
  Develop a financial model to demonstrate the feasibility of constructing and sustaining a regional psychiatric facility
  Facilitate and coordinate the working group’s discussions related to other aspects of the facility, including proposed organization and operations of the facility
  Perform due diligence on alternative solutions to developing a comprehensive, collaborative system of care

## Slide 4: Task 1 – Analytics and Modeling
Tasks to be Performed
  Construct a model for feasibility using national level benchmarks, and state/local data
  Host a focus group to consider design elements for a regional facility
  Conduct key informant interviews with communities that have implemented similar models
Expected Deliverables
  Data analytics report to summarize:
    High utilizers of the ED, specific to psychiatric utilization
    Factors to consider when determining feasibility (i.e. transportation, city policy)
    Predictive analytics to inform estimates on number of resources needed for a regional facility

## Slide 5: Task 2 – Financial Model for Feasibility of Regional Facility
Tasks to be performed
  Convene expert panel to discuss
    Data collected in Task 1
    Design elements needed from the Focus Group
    Community resources needed to meet the requirements for a regional facility
Expected Deliverables
  A convened expert panel
  A topline report of major themes, ideas, and discussions highlighted during the panel

## Slide 6: Task 3 – Facilitate Stakeholder Work Group
Tasks to be performed
  Convene stakeholder work group to identify:
    Organization of a regional facility
    Operations of a regional facility
    Community linkages needed to create a successful comprehensive, collaborative system of care
Expected Deliverables
  Summary report detailing
    Organizational and operational needs for a regional facility
    Community resources to support a facility

## Slide 7: Task 4 – Alternative Solutions
Tasks to be performed
  Convene representatives from the Task Force to provide insights on alternatives to a regional facility
Expected Deliverables
  Pilot plan, including evaluation metrics, to utilize alternative solutions (i.e. telepsychiatry, increased hours at mental health clinics) to reduce the burden on current EDs

## Slide 8: Progress to Date

## Slide 9: Feasibility Model
  SAMHSA National Data
  National Hospital Ambulatory Medical Care Survey
  Healthcare Cost and Utilization Program (HCUP)
  Data request to OHA
  SAMHSA state date
  Franklin Co. Health Map
  Interview with Alameda Co
  Interview with Portland, OR
  Structured questions to review processes and implementation of regional facility
  Transportation
  Policy
  Training and Staff
  Number of facilities
National Data
State/Local Data
Other Communities
Additional factors
Notes: Explain what we are gathering to build a feasibility model for central Ohio.

## Slide 10: Existing Models of Care
Alameda, CA
John George Hospital (JGH)
Portland, OR
Unity Center
  Dedicated psychiatric hospital that accepts all transfers for emergency stabilization
  Goals are to provide timely, emergent care and avoid hospitalization when possible
  Specific billing code established
  Outcomes: transferred to JGH within 2 hours of ED admission, 75% discharged home or to community-based program
  Scheduled to open in 2017
  Initiative to address issues like overcrowding, long waits, a lack of social workers, and few adequate referrals to long-term treatment
  Effort between 4 major health systems
  Will offer crisis stabilization, medication, crisis counseling, family and peer support, and transition-of-care planning
Notes: Explain similarities and differences from two community approaches to regional care.

## Slide 11: Contributing Factors
Patient Use
Insurance Status
Emergency Responders
Transportation
City Policies
Bed Counts
Cost
Staff
Community Resources
Training
Notes: Mapping out factors that impact the flow of ED use for psychiatric care, we are working with national data, and with OHA to get access to local data to fill in gaps with these various factors.

## Slide 12: Analytics Model
Inputs
Patient Demographics and Utilization
Delta
Regional Facility
Alternative Solutions
Outputs
Cost
Utilization
Community Resources
Improved Access to Care
Reduced Boarding Times
Hospital Resources
Notes: Emphasis for this slide: including the contributing factors from the previous slide, we’ll use the data to predict the outputs based on a given delta. Either a regional facility or alternative solutions. Based on the predicted outputs, the Task Force can determine what delta is best for the community.

## Slide 13: Next Steps

## Slide 14: Finish Data Collection
Focus Group
  Design elements needed
  Costing estimates
OHA and other databases
  Establishing current stats
  Test model
  Predict outcomes based on delta
Key Informant Interviews
  Alameda and Portland

## Slide 15: Convene Expert Panel
Desired outcomes for patients
Factors relevant to the community that will impact decision for a regional facility
  Compile major themes and ideas from panel with analytics data for final reports

## Slide 16: Questions?
Mary Sheehan, MPH, RD
sheehanm@battelle.org
Jeff Geppert, JD, MEd
Geppertj@battelle.org